## README
Date	10/14/2019
Author	Hamza Awad, Huzaifah Simjee, Qi Jie Guan, Shreya Kumar, Katherine Legaspi
Email	hawad003@ucr.edu, hsimj001@ucr.edu, qguan001@ucr.edu, skuma021@ucr.edu, klega002@ucr.edu
Team Name	Team 626 - Google Keep
Summary / Requirements	A web-based platform for note-taking developed by Google. On this web app, the user can write, edit, customize, and share their notes. The user can organize their notes by categorizing and archiving their notes. The notes are linked to the user’s gmail account, so it can be accessed and modified everywhere. It can also be shared to other users using their gmail accounts for cooperative note taking.

Tabs	Notes
"Product Backlog"	Should be initialized with the user stories and their estimated efforts (i.e., story points)
	Depending on the amount of story points, some stories may need to be split into smaller stories
	Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)

"Task Board"	To Do is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
	Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
	Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
	Perform task assignments at the Sprint Planning Meeting
	During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
	Inform your teammates know before you pull a task from "To Do" list
	To Verify should be pulled by a different team member; This is a good time to perform code review and unit testing
	A task in "Done" list should have its verifier's name appended

"Archives"	At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting

"Burndown Chart"	At the end of a Sprint, update the "Burndown Chart"
	if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID	Story Name	Story (small features)	Story Points	Priority	Comments
1	Registration	As a user, I would want to create login credentials in order to access the websites functionality. (A.C. When a user first opens the app, they are asked to link their gmail account, and if it is a previously unlinked account, the database will assign to that account a unique user ID.)	3	2
2	Login/Logout	As a user, I would want to log in using my credentials and log out to keep others from manipulating my account's notes. (A.C. After previously registering, a user can use the same gmail account from last time and they will have access to their personal information that they registered with.)	3	3
3	Homepage	As a user, I want to visit the homepage where I can create, delete and display previous notes (UI) (A.C. When a user is logged in, the first page they will be taken to will be a page that displays any notes they creaetd beforehand, note filtering options, and a note creation option)	3	1
4	Add Note/Delete Note	As a user who wants to be organized, I want to create and remove previously made notes. (A.C. Note is created and stored on Firebase, and the user can remove the node which then deletes it from Firebase)	9	1
5	Share Note	As a user who wants to keep memory of something that others and I can access, I want to share my digital note with others’ emails. (A.C. When a user shares their note with an existing gmail account, the recepient of the shared note will have the note appear under the "Shared Notes" side tab)	9	1
6	Edit	As a user who wants to revisit and modify a note, I want to make a change to a note that already exists. (A.C. When a user finishes editting a note using the "edit note" button on a note, the note will update visually with the changes and the database will update the note with the new information and a new timestamp)	5	3
7	Archive	As a user who is done with a note temporarily, I want to temporarily set that note aside from the page. (A.C. When a user clicks on the "Archive Button" on a note, it no longer will appear on the home screen but will instead appear in the sidetab "Archive")	2	4
8	Note Filtering	As a user who wants to find notes that I previously created, I want to process through my list of notes using a filter. (A.C. Filtering with based on most recently created note, and on alpahabetical subject)	6	2
9	Search by Tag	As a user who wants to categorize their notes with custom tag fields, I want to assign my chosen notes into tags and filter through them using a search bar. (A.C. Upon creating a tag and using the tag search feature, only the appropriately tagged notes will appear)	8	2
10	Image Storage	As a user who wants to add photo to their notes, I want to upload an image to a note and have it show. (A.C When a user clicks on the "Image Button" on a note, it displays the user's finder and the user is able to choose an image (.png, .jpg) to uplaod to FIrebase and have it show on the note)	8	6
11	Note Coloring	As a user who wants to be able to visually distinguish between their notes, I want to be able to choose between a set of colors. (A.C. When a user picks a color and submits the mini-form, the note should then refresh with that color. And if the user doesn't pick any color, the note color should be defaulted to white)	6	7

	Total		56

## Task Board
To Do (Sprint Backlog)	In Progress	Testing	Done
			Task 1. A user should be able to share a note to an existing email
			Task 2. A user is able to edit an existing note and save to the database
			Task 3. A note can be directed to archive
			Task 4. Archive button should only display notes that are archived
			Task 5. Add a tag to a note
			Task 6. Search notes by tag
			Task 7: Add upload image/image storage
			Task 8: Note coloring

## Archives
Sprint ID	Scrum Master	Tasks Completed
1	Hamza Awad	Task 1: Connect Firebase to Project (Huzaifah)
		Task 2: Create UI for log-in page (Qi Jie)
		Task 3: Create Login logic using the Google sign-in provision on Firebase (Katherine)
		Task 4: Create logout button functionality (Shreya)
		Task 5: Create UI for homepage (Hamza)
		Task 6: Create UI/registration logic (Huzaifah)

2	Shreya Kumar
		Task 1: A page displays any existing user notes (Katherine)
		Task 2: A user must be able to add a note (Qi Jie)
		Task 3: Add Note should save to database (Hamza)
		Task 4: Sort note displaying based on recency (Huzaifah)
		Task 5: Sort note displaying based on alphabetical note subject (Huzaifah)
		Task 6: A user must be able to delete a note (Shreya)

3	Huzaifah Simjee
		Task 1. A user should be able to share a note to an existing email (Huzaifah)
		Task 2. A user is able to edit an existing note and save to the database (Huzaifah)
		Task 3. A note can be directed to archive (Qi Jie)
		Task 4. Archive button should only display notes that are archived (Shreya)
		Task 5. Add a tag to a note (Hamza)
		Task 6. Search notes by tag (Hamza)
		Task 7: Add upload image/image storage (Katherine)
		Task 8: Note coloring (Katherine)

## Burndown Chart
Sprint ID	Story Points (Total)	Story Points (Completed)	Story Points (Accumulated)	Story Points (Remaining)	Ideal
0	56	-	-	64	64
1	56	9	9	55	42
2	56	15	24	32	21
3	56	32	56	0	0